## Tong quan
BANG THEO DOI TIEN DO - LO TRINH 12 TUAN BLOCKCHAIN DEVELOPER INTERN (RUST / SOLANA)
Ngay bat dau: | 2026-06-18
Ngay ket thuc du kien (84 ngay): | 2026-09-09
TIEN DO TONG QUAN - BLOCKCHAIN
Tong so ngay hoc | 84
So ngay da hoan thanh | 2
So ngay dang lam | 4
% Hoan thanh tong the | 2.381%
Tong so gio da hoc | 3.5
TIEN DO THEO TUAN (Blockchain & DSA)
Tuan | Chu de Blockchain | % Blockchain | Chu de DSA | % DSA
1 | Blockchain Fundamentals | 28.57% | Array & Hashing | 57.14%
2 | Cryptography chuyen sau | 0% | Two Pointers & Sliding Window | 0%
3 | Bitcoin Architecture | 0% | Stack | 0%
4 | Ethereum Architecture | 0% | Binary Search | 0%
5 | Rust nang cao cho on-chain | 0% | Linked List | 0%
6 | Solana Fundamentals (native) | 0% | Trees nhap mon | 0%
7 | Anchor Framework | 0% | Trees nang cao & Heap | 0%
8 | Smart Contract Dev - Escrow | 0% | Backtracking | 0%
9 | SPL Token Program | 0% | Graphs co ban | 0%
10 | NFT Program (Metaplex) | 0% | Graphs nang cao | 0%
11 | DeFi co ban - Staking | 0% | Dynamic Programming 1D | 0%
12 | Portfolio + Interview Prep | 0% | DP 2D + Tong on | 0%
TONG QUAN TRACK DSA
Tong so bai LeetCode | 84
So bai da hoan thanh | 4
So bai dang lam | 2
So bai da bo qua (Hard tuy chon) | 0
% Hoan thanh DSA tong the | 4.762%
PORTFOLIO PROJECTS
Project | Hoan thanh/Tong | % Hoan thanh
anchor-escrow | 0/7 | 0%
anchor-staking-pool | 0/7 | 0%
anchor-nft-minter | 0/6 | 0%
CAU HOI PHONG VAN
Da tu tin tra loi | 0/20

## Theo doi hang ngay
Tuan | Ngay thu | STT (1-84) | Ngay hoc (date) | Chu de chinh (Blockchain) | Tai lieu chinh thuc | Nhiem vu thuc hanh | Trang thai (Blockchain) | So gio hoc | Ghi chu | Chu de DSA tuan | Bai LeetCode (Rust) | Do kho DSA | Trang thai DSA | Ghi chu DSA
1 | 1 | 1 | 2026-06-18 | Decentralization, distributed ledger, block structure | Bitcoin Whitepaper - bitcoin.org/bitcoin.pdf | Viet tom tat 1 trang + ve so do block | Hoan thanh | 1.5 | ghi nho ca keyword tieng anh | Array & Hashing | Two Sum | Easy | Hoan thanh | chu y cac cu phap
1 | 2 | 2 | 2026-06-19 | Cryptographic hash function (SHA-256, Keccak256) | RustCrypto/hashes - github.com/RustCrypto/hashes | Code hash_block() bang crate sha2, test avalanche effect | Hoan thanh | 2 | ghi nho ca keyword tieng anh |  | Contains Duplicate | Easy | Hoan thanh | su dung insert trong HashSet
1 | 3 | 3 | 2026-06-20 | Merkle Tree: cau truc, Merkle proof | Bitcoin Developer Guide - Merkle Trees | Code MerkleTree struct, build proof, verify_proof() | Dang lam |  |  |  | Valid Anagram | Easy | Hoan thanh | su dung sort hay vi sort_unstable
1 | 4 | 4 | 2026-06-21 | Public-key cryptography, digital signature | Cloudflare - ECC primer (blog.cloudflare.com) | Dung ed25519-dalek: generate keypair, sign, verify | Dang lam |  |  |  | Group Anagrams | Medium | Hoan thanh | nho entry, into_values
1 | 5 | 5 | 2026-06-22 | Consensus: PoW, PoS, BFT (gioi thieu Tower BFT) | Ethereum.org - Consensus Mechanisms | Code PoW miner tim nonce thoa target | Dang lam |  |  |  | Top K Frequent Elements | Medium | Dang lam
1 | 6 | 6 | 2026-06-23 | Project ngay: ghep thanh mini blockchain | - | Xay rust-mini-blockchain: block+hash+Merkle+PoW+sign | Dang lam |  |  |  | Product of Array Except Self | Medium | Dang lam
1 | 7 | 7 | 2026-06-24 | Checkpoint tuan 1 | - | Tu quiz + push rust-mini-blockchain len GitHub | Chua bat dau |  |  |  | Valid Sudoku | Medium | Chua bat dau
2 | 1 | 8 | 2026-06-25 | ECC truc giac, duong cong secp256k1 | SEC2 spec - secg.org/sec2-v2.pdf | Ve so do point addition tren duong cong | Chua bat dau |  |  | Two Pointers & Sliding Window | Valid Palindrome | Easy | Chua bat dau
2 | 2 | 9 | 2026-06-26 | secp256k1 (BTC/ETH) vs ed25519 (Solana) | Solana Docs - Keys & Wallets | Tao keypair bang solana-keygen, verify | Chua bat dau |  |  |  | Two Sum II - Input Array Is Sorted | Easy | Chua bat dau
2 | 3 | 10 | 2026-06-27 | Address derivation (Bitcoin/Ethereum/Solana) | Ethereum.org - Accounts | Tu tinh address ETH tu public key bang Rust | Chua bat dau |  |  |  | 3Sum | Medium | Chua bat dau
2 | 4 | 11 | 2026-06-28 | BIP32/BIP39/BIP44 - mnemonic, HD wallet | BIP-39 spec (github bitcoin/bips) | Dung crate bip39 sinh mnemonic, derive Solana keypair | Chua bat dau |  |  |  | Container With Most Water | Medium | Chua bat dau
2 | 5 | 12 | 2026-06-29 | Transaction signing flow tong quat | Solana Docs - Transactions | Code Transaction struct + sign()/verify() doc lap | Chua bat dau |  |  |  | Best Time to Buy and Sell Stock | Easy | Chua bat dau
2 | 6 | 13 | 2026-06-30 | Project ngay: Wallet CLI tool | - | Xay rust-wallet-cli: gen keypair, sign, verify, address | Chua bat dau |  |  |  | Longest Substring Without Repeating Characters | Medium | Chua bat dau
2 | 7 | 14 | 2026-07-01 | Checkpoint tuan 2 | - | Quiz + push rust-wallet-cli len GitHub | Chua bat dau |  |  |  | Longest Repeating Character Replacement | Medium | Chua bat dau
3 | 1 | 15 | 2026-07-02 | UTXO model vs Account model | Bitcoin Developer Guide - Transactions | Ve so do UTXO input/output | Chua bat dau |  |  | Stack | Valid Parentheses | Easy | Chua bat dau
3 | 2 | 16 | 2026-07-03 | Cau truc transaction Bitcoin (scriptSig/scriptPubKey) | Bitcoin Developer Reference - Transactions | Decode raw tx hex bang crate bitcoin (rust-bitcoin) | Chua bat dau |  |  |  | Min Stack | Medium | Chua bat dau
3 | 3 | 17 | 2026-07-04 | Block header, mining difficulty, Merkle root | Bitcoin Developer Guide - Block Chain | Lay block thuc qua Blockstream API, tu tinh lai Merkle root | Chua bat dau |  |  |  | Evaluate Reverse Polish Notation | Medium | Chua bat dau
3 | 4 | 18 | 2026-07-05 | Bitcoin Script co ban, multisig (P2SH) | Bitcoin Script wiki (en.bitcoin.it/wiki/Script) | Viet vi du OP_2 OP_3 OP_CHECKMULTISIG, giai thich flow | Chua bat dau |  |  |  | Generate Parentheses | Medium | Chua bat dau
3 | 5 | 19 | 2026-07-06 | Lightning Network tong quan | Lightning Network whitepaper | Tom tat 5 cau payment channel giai quyet van de gi | Chua bat dau |  |  |  | Daily Temperatures | Medium | Chua bat dau
3 | 6 | 20 | 2026-07-07 | Project ngay: Bitcoin tx parser | - | Xay bitcoin-tx-parser CLI in JSON inputs/outputs/fee | Chua bat dau |  |  |  | Car Fleet | Medium | Chua bat dau
3 | 7 | 21 | 2026-07-08 | Checkpoint tuan 3 | - | Quiz UTXO vs Account + push bitcoin-tx-parser | Chua bat dau |  |  |  | Largest Rectangle in Histogram | Hard (tuy chon) | Chua bat dau
4 | 1 | 22 | 2026-07-09 | Account model, World State (Merkle Patricia Trie) | Ethereum.org - Accounts | So sanh bang UTXO/Account/Solana (ban draft) | Chua bat dau |  |  | Binary Search | Binary Search | Easy | Chua bat dau
4 | 2 | 23 | 2026-07-10 | EVM: bytecode, opcode, gas, execution model | Ethereum.org - EVM | Deploy contract counter qua Remix len Sepolia testnet | Chua bat dau |  |  |  | Search a 2D Matrix | Medium | Chua bat dau
4 | 3 | 24 | 2026-07-11 | ERC-20 / ERC-721 interface (doc hieu) | EIP-20, EIP-721 (eips.ethereum.org) | Doc interface, ghi chu so sanh voi SPL Token | Chua bat dau |  |  |  | Koko Eating Bananas | Medium | Chua bat dau
4 | 4 | 25 | 2026-07-12 | Gas mechanics, EIP-1559 (base fee + priority fee) | Ethereum.org - Gas | Tu tinh vi du phi gas thuc te | Chua bat dau |  |  |  | Find Minimum in Rotated Sorted Array | Medium | Chua bat dau
4 | 5 | 26 | 2026-07-13 | So sanh kien truc Bitcoin vs Ethereum vs Solana | Solana Docs (solana.com/docs) | Viet file comparison.md day du | Chua bat dau |  |  |  | Search in Rotated Sorted Array | Medium | Chua bat dau
4 | 6 | 27 | 2026-07-14 | Project ngay: Rust client query Ethereum testnet | - | Dung ethers-rs/alloy query balance + latest block Sepolia | Chua bat dau |  |  |  | Time Based Key-Value Store | Medium | Chua bat dau
4 | 7 | 28 | 2026-07-15 | Checkpoint tuan 4 | - | Quiz so sanh kien truc + hoan thien comparison.md | Chua bat dau |  |  |  | Median of Two Sorted Arrays | Hard (tuy chon) | Chua bat dau
5 | 1 | 29 | 2026-07-16 | Borsh serialization - vi sao Solana dung Borsh | Borsh specification - borsh.io | Derive BorshSerialize/Deserialize, in ra bytes | Chua bat dau |  |  | Linked List | Reverse Linked List | Easy | Chua bat dau
5 | 2 | 30 | 2026-07-17 | Generic vs dyn Trait (anh huong compute unit) | Rust Book Ch.10 & Ch.17 (doc.rust-lang.org/book) | So sanh binary size bang cargo bloat | Chua bat dau |  |  |  | Merge Two Sorted Lists | Easy | Chua bat dau
5 | 3 | 31 | 2026-07-18 | Memory layout: #[repr(C)], alignment/padding | Rust Reference - Type Layout | Kiem tra size_of/align_of truoc/sau khi them repr(C) | Chua bat dau |  |  |  | Reorder List | Medium | Chua bat dau
5 | 4 | 32 | 2026-07-19 | Macro co ban: macro_rules! | Rust Book Ch.19.5 - Macros | Viet macro tu sinh ham getter/setter cho struct | Chua bat dau |  |  |  | Remove Nth Node From End of List | Medium | Chua bat dau
5 | 5 | 33 | 2026-07-20 | Error handling: thiserror vs ProgramError | thiserror docs (docs.rs/thiserror) | Refactor code Axum cu dung thiserror | Chua bat dau |  |  |  | Add Two Numbers | Medium | Chua bat dau
5 | 6 | 34 | 2026-07-21 | Project ngay: Borsh playground + benchmark | - | Repo borsh-playground: unit test + benchmark criterion | Chua bat dau |  |  |  | Copy List with Random Pointer | Medium | Chua bat dau
5 | 7 | 35 | 2026-07-22 | Checkpoint tuan 5 | - | Quiz vi sao tranh Box/Rc on-chain + push borsh-playground | Chua bat dau |  |  |  | Linked List Cycle | Easy | Chua bat dau
6 | 1 | 36 | 2026-07-23 | Solana account model: executable vs data, rent | Solana Docs - Accounts | Xem 1 account thuc qua CLI 'solana account <address>' | Chua bat dau |  |  | Trees nhap mon | Invert Binary Tree | Easy | Chua bat dau
6 | 2 | 37 | 2026-07-24 | Transaction & Instruction structure | Solana Docs - Transactions | Ve so do 1 transaction nhieu instruction | Chua bat dau |  |  |  | Maximum Depth of Binary Tree | Easy | Chua bat dau
6 | 3 | 38 | 2026-07-25 | Program Derived Address (PDA): derive, bump seed | Solana Docs - PDA | Code find_program_address voi nhieu seed khac nhau | Chua bat dau |  |  |  | Same Tree | Easy | Chua bat dau
6 | 4 | 39 | 2026-07-26 | Cross-Program Invocation (CPI) - tong quan | Solana Docs - CPI | Doc source SPL Token program phan invoke() | Chua bat dau |  |  |  | Subtree of Another Tree | Easy | Chua bat dau
6 | 5 | 40 | 2026-07-27 | Setup moi truong: solana-test-validator, CLI toolchain | Solana Docs - Installation | Cai Solana CLI, chay local validator, airdrop SOL | Chua bat dau |  |  |  | Lowest Common Ancestor of a BST | Medium | Chua bat dau
6 | 6 | 41 | 2026-07-28 | Project ngay: Native Counter Program (khong Anchor) | - | Repo solana-native-counter: Initialize+Increment, deploy local | Chua bat dau |  |  |  | Binary Tree Level Order Traversal | Medium | Chua bat dau
6 | 7 | 42 | 2026-07-29 | Checkpoint tuan 6 | - | Quiz flow transaction toan dien + push solana-native-counter | Chua bat dau |  |  |  | Validate Binary Search Tree | Medium | Chua bat dau
7 | 1 | 43 | 2026-07-30 | Cai dat Anchor, cau truc project, Anchor.toml, IDL | Anchor Docs - Installation (anchor-lang.com) | anchor init, anchor build, xem file IDL sinh ra | Chua bat dau |  |  | Trees nang cao & Heap | Binary Tree Right Side View | Medium | Chua bat dau
7 | 2 | 44 | 2026-07-31 | Macro #[program], instruction handler, Context<T> | Anchor Docs - Program Module | Viet lai Counter Program (tuan 6) bang Anchor | Chua bat dau |  |  |  | Construct Binary Tree from Preorder and Inorder Traversal | Medium | Chua bat dau
7 | 3 | 45 | 2026-08-01 | #[derive(Accounts)]: init, payer, space, seeds, bump, has_one | Anchor Docs - Account Constraints | Them PDA vao Counter Program, dung seeds/bump | Chua bat dau |  |  |  | Kth Smallest Element in a BST | Medium | Chua bat dau
7 | 4 | 46 | 2026-08-02 | Custom error #[error_code], su kien emit! | Anchor Docs - Errors | Them custom error thay cho panic! | Chua bat dau |  |  |  | Kth Largest Element in an Array | Medium | Chua bat dau
7 | 5 | 47 | 2026-08-03 | Testing Anchor bang TypeScript (Mocha) | Anchor Docs - Testing | Viet tests/counter.ts: happy path + 1 case loi | Chua bat dau |  |  |  | Last Stone Weight | Easy | Chua bat dau
7 | 6 | 48 | 2026-08-04 | Project ngay: hoan thien Anchor Counter | - | Repo anchor-counter: Init/Inc/Dec/Reset + test + README | Chua bat dau |  |  |  | K Closest Points to Origin | Medium | Chua bat dau
7 | 7 | 49 | 2026-08-05 | Checkpoint tuan 7 | - | Quiz Anchor tu dong validate gi + push anchor-counter | Chua bat dau |  |  |  | Top K Frequent Elements (lam lai) | Medium | Chua bat dau
8 | 1 | 50 | 2026-08-06 | Thiet ke Escrow program: use-case, account/state | Anchor + SPL Token Docs | Ve so do account EscrowState/Vault/Initializer/Taker | Chua bat dau |  |  | Backtracking | Subsets | Medium | Chua bat dau
8 | 2 | 51 | 2026-08-07 | Implement initialize_escrow + CPI transfer vao vault | Anchor Docs - CPI | Code initialize, dung anchor_spl::token::transfer | Chua bat dau |  |  |  | Combination Sum | Medium | Chua bat dau
8 | 3 | 52 | 2026-08-08 | Implement exchange (taker doi token) | - | Code exchange voi has_one, kiem tra amount khop | Chua bat dau |  |  |  | Permutations | Medium | Chua bat dau
8 | 4 | 53 | 2026-08-09 | Implement cancel (initializer rut lai) | - | Code cancel, dam bao chi initializer moi cancel duoc | Chua bat dau |  |  |  | Word Search | Medium | Chua bat dau
8 | 5 | 54 | 2026-08-10 | Viet test day du: happy path + cac case fail | Anchor Docs - Testing | Viet >=5 test case trong tests/escrow.ts | Chua bat dau |  |  |  | Letter Combinations of a Phone Number | Medium | Chua bat dau
8 | 6 | 55 | 2026-08-11 | Security review: overflow, signer check, ownership | github.com/coral-xyz/sealevel-attacks | Ra soat code theo checklist sealevel-attacks, fix lo hong | Chua bat dau |  |  |  | Palindrome Partitioning | Medium | Chua bat dau
8 | 7 | 56 | 2026-08-12 | Checkpoint tuan 8 - Portfolio Project #1 | - | Deploy devnet, demo script, push anchor-escrow + README | Chua bat dau |  |  |  | N-Queens | Hard (tuy chon) | Chua bat dau
9 | 1 | 57 | 2026-08-13 | SPL Token: Mint account, Token account, ATA | SPL Token Docs (spl.solana.com/token) | Ghi chu khac biet SPL Token vs ERC-20 | Chua bat dau |  |  | Graphs co ban | Number of Islands | Medium | Chua bat dau
9 | 2 | 58 | 2026-08-14 | Thuc hanh CLI: tao token, mint, transfer | Solana Docs - spl-token CLI | create-token, create-account, mint, transfer tren devnet | Chua bat dau |  |  |  | Clone Graph | Medium | Chua bat dau
9 | 3 | 59 | 2026-08-15 | Implement Anchor: create_mint, mint_to (anchor-spl) | Anchor SPL docs (docs.rs/anchor-spl) | Viet instruction create_mint va mint_tokens | Chua bat dau |  |  |  | Max Area of Island | Medium | Chua bat dau
9 | 4 | 60 | 2026-08-16 | Token-2022 (Token Extensions) tong quan | Solana Docs - Token Extensions | Doc & ghi chu 3 extension pho bien nhat | Chua bat dau |  |  |  | Pacific Atlantic Water Flow | Medium | Chua bat dau
9 | 5 | 61 | 2026-08-17 | Thiet ke Token Faucet (cooldown chong spam) | - | Thiet ke FaucetConfig PDA + last_claim_timestamp | Chua bat dau |  |  |  | Course Schedule | Medium | Chua bat dau
9 | 6 | 62 | 2026-08-18 | Project ngay: Implement & test Token Faucet | - | Repo spl-token-faucet: initialize_faucet, claim_token + test | Chua bat dau |  |  |  | Number of Connected Components in an Undirected Graph | Medium | Chua bat dau
9 | 7 | 63 | 2026-08-19 | Checkpoint tuan 9 - Portfolio Project #2 (ung vien) | - | Quiz vi sao can ATA + push spl-token-faucet | Chua bat dau |  |  |  | Redundant Connection | Medium | Chua bat dau
10 | 1 | 64 | 2026-08-20 | NFT tren Solana: Metadata Account, Master Edition | Metaplex Docs - Token Metadata | Doc so do Mint + Metadata account | Chua bat dau |  |  | Graphs nang cao | Course Schedule II | Medium | Chua bat dau
10 | 2 | 65 | 2026-08-21 | Thuc hanh mint NFT qua SDK/CLI (cam nhan flow) | Metaplex Sugar CLI / Umi SDK | Mint 1 NFT test tren devnet, xem Solana Explorer | Chua bat dau |  |  |  | Network Delay Time | Medium | Chua bat dau
10 | 3 | 66 | 2026-08-22 | Implement CPI mint_nft trong Anchor program | Metaplex Token Metadata Rust SDK | Code mint_nft: tao mint + CPI metadata + master edition | Chua bat dau |  |  |  | Cheapest Flights Within K Stops | Medium | Chua bat dau
10 | 4 | 67 | 2026-08-23 | Candy Machine - tong quan kien truc | Metaplex Docs - Candy Machine | Doc & ghi chu flow config line/guard/mint | Chua bat dau |  |  |  | Min Cost to Connect All Points | Medium | Chua bat dau
10 | 5 | 68 | 2026-08-24 | Hoan thien metadata: royalty, creators array | - | Bo sung seller_fee_basis_points, creators | Chua bat dau |  |  |  | Word Ladder | Hard (tuy chon) | Chua bat dau
10 | 6 | 69 | 2026-08-25 | Project ngay: Test & deploy NFT Minter | - | Repo anchor-nft-minter: test mint, verify tren Explorer | Chua bat dau |  |  |  | Alien Dictionary | Hard (tuy chon) | Chua bat dau
10 | 7 | 70 | 2026-08-26 | Checkpoint tuan 10 - Portfolio Project #3 (ung vien) | - | Quiz NFT vs Fungible Token + push anchor-nft-minter | Chua bat dau |  |  |  | Surrounded Regions | Medium | Chua bat dau
11 | 1 | 71 | 2026-08-27 | AMM: constant product formula x*y=k, slippage | Uniswap V2 Whitepaper | Tu tinh vi du swap bang tay theo cong thuc | Chua bat dau |  |  | Dynamic Programming 1D | Climbing Stairs | Easy | Chua bat dau
11 | 2 | 72 | 2026-08-28 | Solana DeFi: Raydium (AMM), Orca (concentrated liquidity) | Orca Docs (docs.orca.so) | Ghi chu khac biet AMM thuong vs Whirlpool | Chua bat dau |  |  |  | House Robber | Medium | Chua bat dau
11 | 3 | 73 | 2026-08-29 | Lending/Borrowing: collateral, health factor, liquidation | Solend/Kamino Docs | Ghi chu flow deposit-borrow-liquidation | Chua bat dau |  |  |  | House Robber II | Medium | Chua bat dau
11 | 4 | 74 | 2026-08-30 | Thiet ke Staking Pool (reward theo thoi gian) | - | Thiet ke StakePool/UserStake (PDA theo user) | Chua bat dau |  |  |  | Longest Increasing Subsequence | Medium | Chua bat dau
11 | 5 | 75 | 2026-08-31 | Implement stake + tinh reward (checked_add/mul) | Solana Docs - Program Security | Code stake, update_rewards | Chua bat dau |  |  |  | Coin Change | Medium | Chua bat dau
11 | 6 | 76 | 2026-09-01 | Project ngay: claim_rewards, unstake + test | - | Repo anchor-staking-pool: hoan thien 4 instruction + test | Chua bat dau |  |  |  | Maximum Subarray | Medium | Chua bat dau
11 | 7 | 77 | 2026-09-02 | Checkpoint tuan 11 | - | Quiz vi sao dung checked_* + push anchor-staking-pool | Chua bat dau |  |  |  | Word Break | Medium | Chua bat dau
12 | 1 | 78 | 2026-09-03 | Chon & polish 3 project portfolio tot nhat | - | Viet lai README chuan cho 3 repo (kien truc, cach chay) | Chua bat dau |  |  | DP 2D + Tong on | Unique Paths | Medium | Chua bat dau
12 | 2 | 79 | 2026-09-04 | Them CI/CD don gian (GitHub Actions) | GitHub Actions docs | Them workflow chay anchor build/test tu dong | Chua bat dau |  |  |  | Longest Common Subsequence | Medium | Chua bat dau
12 | 3 | 80 | 2026-09-05 | Demo truc quan (GIF/video ngan) | - | Quay demo tung project, nhung vao README | Chua bat dau |  |  |  | Edit Distance | Medium (tuy chon) | Chua bat dau
12 | 4 | 81 | 2026-09-06 | On tap tong hop toan bo 11 tuan | - | Doc lai comparison.md, sealevel-attacks, cac quiz cu | Chua bat dau |  |  |  | Merge Intervals | Medium | Chua bat dau
12 | 5 | 82 | 2026-09-07 | Luyen 20 cau hoi phong van | - | Tu tra loi thanh tieng, ghi am, nghe lai, rut gon | Chua bat dau |  |  |  | Tu chon 1 bai lam sai/cham nhat truoc do | - | Chua bat dau
12 | 6 | 83 | 2026-09-08 | Mock interview + live coding nho | - | Tu dat de viet 1 instruction Anchor trong 20-25 phut | Chua bat dau |  |  |  | Mock interview: 1 bai Medium ngau nhien, bam gio 35-40p | - | Chua bat dau
12 | 7 | 84 | 2026-09-09 | Checkpoint cuoi cung | - | Chay qua checklist ky nang, chuan bi CV, apply | Chua bat dau |  |  |  | Tong ket track DSA | - | Chua bat dau
Formulas:
Ngay hoc (date) = 'Tong quan'!$B3+([STT (1-84)]-1)

## Checkpoint theo tuan
Tuan | Chu de chinh (Blockchain) | Tieu chi checkpoint | Da hoan thanh ngay 7? | Dat / Chua dat | Chu de DSA tuan nay | % DSA hoan thanh tuan | Ghi chu
1 | Blockchain Fundamentals | Giai thich duoc hash/Merkle/PoW, code rust-mini-blockchain chay duoc | Chua bat dau | Chua dat | Array & Hashing | 57.14%
2 | Cryptography chuyen sau | Tu tao keypair, sign/verify thanh thao, rust-wallet-cli hoan chinh | Chua bat dau | Chua dat | Two Pointers & Sliding Window | 0%
3 | Bitcoin Architecture | Hieu UTXO, parse duoc raw Bitcoin transaction | Chua bat dau | Chua dat | Stack | 0%
4 | Ethereum Architecture | Hieu EVM/gas, viet xong file so sanh BTC/ETH/Solana | Chua bat dau | Chua dat | Binary Search | 0%
5 | Rust nang cao cho on-chain | Thanh thao Borsh, hieu memory layout, benchmark xong | Chua bat dau | Chua dat | Linked List | 0%
6 | Solana Fundamentals (native) | Tu viet duoc native Solana program, hieu PDA/CPI co ban | Chua bat dau | Chua dat | Trees nhap mon | 0%
7 | Anchor Framework | Tu viet Anchor program tu dau khong copy template | Chua bat dau | Chua dat | Trees nang cao & Heap | 0%
8 | Smart Contract Dev - Escrow | anchor-escrow deploy devnet thanh cong, qua security review | Chua bat dau | Chua dat | Backtracking | 0%
9 | SPL Token Program | spl-token-faucet hoat dong dung, hieu ro ATA | Chua bat dau | Chua dat | Graphs co ban | 0%
10 | NFT Program (Metaplex) | anchor-nft-minter mint thanh cong, metadata hien dung tren Explorer | Chua bat dau | Chua dat | Graphs nang cao | 0%
11 | DeFi co ban - Staking | anchor-staking-pool tinh reward dung, khong overflow | Chua bat dau | Chua dat | Dynamic Programming 1D | 0%
12 | Portfolio + Interview Prep | 3 portfolio hoan chinh, tra loi tron 20 cau hoi phong van | Chua bat dau | Chua dat | DP 2D + Tong on | 0%

## Portfolio Projects
Project | Milestone | Trang thai | Ghi chu | TONG HOP TIEN DO PROJECT
anchor-escrow | Thiet ke account/state (EscrowState, Vault) | Chua bat dau |  | Project | Hoan thanh / Tong | % Hoan thanh
anchor-escrow | Implement initialize_escrow + CPI transfer vao vault | Chua bat dau |  | anchor-escrow | 0/7 | 0%
anchor-escrow | Implement exchange | Chua bat dau |  | anchor-staking-pool | 0/7 | 0%
anchor-escrow | Implement cancel | Chua bat dau |  | anchor-nft-minter | 0/6 | 0%
anchor-escrow | Viet test day du (happy path + fail cases) | Chua bat dau
anchor-escrow | Security review theo checklist sealevel-attacks | Chua bat dau
anchor-escrow | Deploy devnet + README hoan chinh | Chua bat dau
anchor-staking-pool | Thiet ke StakePool / UserStake (PDA) | Chua bat dau
anchor-staking-pool | Implement initialize_pool | Chua bat dau
anchor-staking-pool | Implement stake + update_rewards (checked_*) | Chua bat dau
anchor-staking-pool | Implement claim_rewards | Chua bat dau
anchor-staking-pool | Implement unstake | Chua bat dau
anchor-staking-pool | Test day du (stake/claim/unstake) | Chua bat dau
anchor-staking-pool | Deploy devnet + README hoan chinh | Chua bat dau
anchor-nft-minter | Doc & hieu Metaplex Token Metadata | Chua bat dau
anchor-nft-minter | Implement mint_nft (tao mint + CPI metadata) | Chua bat dau
anchor-nft-minter | Them Master Edition | Chua bat dau
anchor-nft-minter | Them royalty / creators array | Chua bat dau
anchor-nft-minter | Test + verify tren Solana Explorer | Chua bat dau
anchor-nft-minter | Deploy devnet + README hoan chinh | Chua bat dau

## Cau hoi phong van
STT | Nhom | Cau hoi | Da tu tin tra loi? | Ghi chu / Diem can cai thien | So cau da tu tin
1 | Fundamentals | Blockchain la gi, khac gi database phan tan thong thuong? | Chua |  | 0/20
2 | Fundamentals | Hash function co tinh chat gi? Vi sao quan trong voi blockchain? | Chua
3 | Fundamentals | Digital signature hoat dong nhu the nao? Phan biet voi ma hoa (encryption)? | Chua
4 | Fundamentals | Merkle Tree dung de lam gi trong blockchain? | Chua
5 | Bitcoin/Ethereum | UTXO model khac Account model nhu the nao? Uu nhuoc diem moi loai? | Chua
6 | Bitcoin/Ethereum | EVM la gi? Gas dung de lam gi? | Chua
7 | Bitcoin/Ethereum | ERC-20 va ERC-721 khac nhau o diem gi? | Chua
8 | Solana core | Vi sao Solana dat throughput cao hon Ethereum L1? | Chua
9 | Solana core | Account model cua Solana hoat dong ra sao? Khac Ethereum the nao? | Chua
10 | Solana core | PDA (Program Derived Address) la gi, dung de lam gi? | Chua
11 | Solana core | Rent tren Solana la gi? | Chua
12 | Solana core | CPI (Cross-Program Invocation) la gi? Cho vi du thuc te. | Chua
13 | Solana core | Compute budget / compute unit la gi? Tai sao phai quan tam? | Chua
14 | Anchor & Smart Contract | Anchor giup gi so voi viet native Solana program? | Chua
15 | Anchor & Smart Contract | #[account(init, payer, space)] trong Anchor lam gi? | Chua
16 | Anchor & Smart Contract | Anchor dung discriminator de lam gi? | Chua
17 | Anchor & Smart Contract | Neu 3 lo hong bao mat pho bien trong Solana program va cach phong tranh. | Chua
18 | Token/NFT/DeFi | SPL Token khac ERC-20 o diem gi ve kien truc? | Chua
19 | Token/NFT/DeFi | NFT tren Solana duoc cau truc nhu the nao (Metaplex)? | Chua
20 | Token/NFT/DeFi | AMM hoat dong theo cong thuc nao? Impermanent loss la gi? | Chua